## Project plan
Project Name | Con Fusion Restaurent
Project Manager | Lokesh Borra
Project Deliverable
Scope Statement:
Start Date | 2017-01-12
End Date | 2017-04-24
Overall Progress
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Lokesh Borra | 2017-01-12 | 2017-01-14 | 2 | Complete
Agree on objectives | Lokesh Borra | 2017-01-15 | 2017-01-17 | 2 | Complete
Detailed Reqs. | Lokesh Borra | 2017-01-18 | 2017-01-21 | 3 | Complete
Hardward Reqs. | Lokesh Borra | 2017-01-18 | 2017-01-21 | 3 | Complete
Final Resource Plan | Lokesh Borra | 2017-01-22 | 2017-01-24 | 2 | Complete
Staffing | Lokesh Borra | 2017-01-24 | 2017-01-25 | 1 | Complete
Techincal Reqs. | Raj Katira | 2017-01-26 | 2017-01-29 | 3 | Complete
Login Option | Raj Katira | 2017-01-30 | 2017-02-06 | 7 | Complete
Reserve Table | Raj Katira | 2017-02-07 | 2017-02-14 | 7 | Complete
Contact Page | Raj Katira | 2017-02-15 | 2017-02-18 | 3 | Complete
Drop Down Menu | Raj Katira | 2017-02-19 | 2017-02-22 | 3 | Complete
About Page | Raj Katira | 2017-02-23 | 2017-02-25 | 2 | Complete
Hardware Config. | Lokesh Borra | 2017-03-15 | 2017-03-26 | 11 | Complete
System Testing | Lokesh Borra | 2017-03-27 | 2017-04-07 | 11 | Complete
Launch |  | 2017-04-24 | 2017-04-24

## StakeHolder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
Lokesh Borra | VP of Product | Final approval of milestones | lokesh.borra30996@gmail.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter
Raj Katira | Business Analyst | Collects the Requirements | rajkatira.5@gmail.com | Query the customer to find the exact requirements of the project | Deal the customer by querying him to find his exact requirements
Raj Katira | Design | Deals with high level and low level design | rajkatira.5@gmail.com | Design for the project considering the input as requirements | Design the project within the planned time
Lokesh Borra | Project Manager | Manages the project and revise the product | lokesh.borra30996@gmail.com | Follow the entire team till the completion of the project | Maintain and help the team whenever problem occurs in the project team